## Sheet1
WBS | Work Packages and Activities | Sponsor (Hamil HC) | Project Manager(Lukas Schmidt) | Project Manager(Yoshito Mizugame) | Paving and Concrete Contractor (Ralph Blasingame) | Paving and Concrete Contractor (Fujimaro Fujii) | Surveyor (Mingyu Zhurong) | Electrician (Darren Lobendahn) | Plumber (Zihao Nangong)
1 | Site Preparation
1.1 | Surveying | I | A, C | A, C |  |  | R, A
1.2 | Grading and clearing | I | A, C | A, C | R, A
1.3 | Roadway development | I | A, C | A, C |  | R, A
1.4 | Apply first coat of asphalt | I | A, C | A, C | R, A | R, A
1.5 | Apply second cost of asphalt | I | A, C | A, C | R, A | R, A
2 | General Conditions
2.1 | Finalize plans and develop estimates | I | A, C | A, C, R
2.2 | Sign contract and notice to proceed | I | A, C, R | A, C
2.3 | Apply for all permits | I | A, C | A, C, R
2.4 | Install temporary power service | I | A, C | A, C |  |  |  | R, A
2.5 | Install underground utilities | I | A, C | A, C |  |  |  |  | R, A
3 | Foundation
3.1 | Excavate for foundation | I | A, C | A, C | R, A | R, A
3.2 | Form basement walls | I | A, C | A, C | R, A | R, A
3.3 | Pour concrete for foundation | I | A, C | A, C | R, A | R, A
3.4 | Waterproof/insulate basement walls | I | A, C | A, C | R, A | R, A
3.5 | Perform foundation inspection | I | A, C | A, C | R, A | R, A