## Sheet1
Stakeholder Analysis Register
Stakeholder Names and Roles | How Important? (L-M-H) | Current level of support (L-M-H) | Needs from Stakeholders | What is important to stakeholders? | Stakeholder Blocks | Stakeholder support Strategy
Jack Skellington - Father | High | High | Notifying neighborhood and law enforcement of this huge party. | Making sure Mom is happy with the party, and showing responsibility in planning and execution. | No property damage and no one is allowed in parent's room during the party. | Getting a job to help support the family and pay for some party costs.
Laurie Strode - Mother | High | High | Funds for DJ and bouncy castle as well as permission to use the backyard | Help to plan setup, brainstorm party activities, after party cleanup, and remembering to include the parents in the party. | Rules applied to the party like shutting down at 1 AM and keeping down noise. | Support with party planning. Gutter cleaning, power washing the siding, and calling Grandma.
Joji - DJ | High | Medium | Bringing soundsystem and and their services for 3 hours. | Help setting up and providing drink, food, and upfront payment. | Failure to show up and DJ. Playing music too loud or too weird. | Scheduling in advance and upfront payment. Tips encouraged. Support during the party to ensure needs are met.
R.J. Macready- Bouncy Castle Provider Family friend | Medium | Medium | Bouncy castle setup and install. | No damage to castle and the return of equipment within a week | Bouncy Castles are out of stock or the one provided is damaged. No assistance in setup or unexpected charges. | Contact a month prior to schedule bouncy castle use. Upfront cash deposit. Support wherever needed in setup process and on time return.
Wilford Brimley - Party goer/bff | Low | Low | Attendance and reasonable behavior during the party. | Good music, food, drinks, games, and friends | Being too rowdy or mean to other guests. Chance they don't attend. | Invite sent out to everyone a month in advance to people we're friendly or aquainted with. Food, drink, and games provided by us.
Michael Myers - Neighbor | Low | Low | Notice prior to party and volume kept down to a reasonable level. | No one bothers him during the party or goes onto his property. | Calls the police on us, crashes the party, or starts killing. | Ample notice of party given and low enough volume so he can watch his soaps in peace.